## Defect Log
AI Code Reviewer — Defect Tracker
Sl No | Defect ID | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type of Defect | Action Taken | Action Taken Date | Status
1 | DEF-001 | BINSIKA | 2026-02-05 | Unused imports were not being detected correctly for certain Python files — AST visitor skipped aliased imports | Sprint 1 | Self | Logical | Improved AST traversal logic in error_detector.py to correctly identify aliased unused imports using visit_Import and visit_ImportFrom | 2026-02-05 | Closed
2 | DEF-002 | BINSIKA | 2026-03-09 | PEP8 style violations were not highlighted consistently in the output — line-length check was missing | Sprint 1 | Self | Standards | Integrated stricter PEP8 line-length checks and improved formatting rule output in error_detector.py | 2026-03-14 | Closed
3 | DEF-003 | BINSIKA | 2026-02-10 | Bare 'except:' clause detection was throwing false positives on try-except-else blocks | Sprint 1 | Self | Logical | Added contextual check using AST node handler attribute to verify bare except before flagging | 2026-02-11 | Closed
4 | DEF-004 | BINSIKA | 2026-02-16 | Groq API returning 429 rate-limit errors during rapid consecutive code submissions from the UI | Sprint 2 | Self | Others | Added exponential back-off retry logic in ai_suggester.py and user-visible 'AI busy' status message | 2026-02-18 | Closed
5 | DEF-005 | BINSIKA | 2026-02-17 | Reflex State variable 'static_results' not updating on second analysis if same code was re-submitted | Sprint 2 | Self | Logical | Forced state reset at the start of run_full_review() to clear previous results before yield | 2026-02-18 | Closed
6 | DEF-006 | BINSIKA | 2026-02-20 | Side-by-side comparison pane not rendering corrected code for JavaScript submissions — showed empty box | Sprint 2 | Self | User Interface | Fixed conditional rx.cond logic in posts() page; corrected_code state variable was not bound to JS result path | 2026-02-22 | Closed
7 | DEF-007 | BINSIKA | 2026-03-03 | Quality grade displayed 'N/A' after successful analysis — grade state variable not reset between sessions | Sprint 3 | Self | User Interface | Initialized grade state to empty string and updated gradeFromIssues() to always return a valid letter | 2026-03-04 | Closed
8 | DEF-008 | BINSIKA | 2026-03-05 | AI summary JSON response from Groq occasionally contained markdown fences causing JSON.parse() failure | Sprint 3 | Self | Logical | Added .replace('```json','').replace('```','').strip() sanitization in ai_suggester.py before JSON.parse | 2026-03-06 | Closed
9 | DEF-009 | BINSIKA | 2026-03-09 | FastAPI server on Windows throwing WinError 10013 (socket permission) on host 0.0.0.0 | Sprint 3 | Self | Others | Changed server host to 127.0.0.1 in server.py; updated API_URL in main.py to match | 2026-03-09 | Closed
10 | DEF-010 | BINSIKA | 2026-03-16 | Review History page showing all cards collapsed with no expand toggle — on_click lambda not bound to index | Sprint 4 | Self | User Interface | Refactored toggle_history_item() to accept index parameter; updated rx.foreach loop to pass idx correctly | 2026-03-17 | Closed
11 | DEF-011 | BINSIKA | 2026-03-20 | Variable context (code_visitor) showing Python builtins like 'print' and 'len' as created variables | Sprint 4 | Self | Logical | Expanded PYTHON_BUILTINS frozenset in error_detector.py to exclude all standard built-in names | 2026-03-21 | Closed
12 | DEF-012 | BINSIKA | 2026-03-25 | PDF report download opens blank page on some Chrome versions — window.print() not triggered after content load | Sprint 4 | Self | User Interface | Wrapped window.print() in setTimeout(500ms) to allow DOM to fully render before printing | 2026-03-26 | Open
TOTAL DEFECTS: 12 |  |  |  | Closed: 11 Open: 1 |  |  |  | 92% closure rate

## Dashboard
Defect Dashboard — AI Code Reviewer
Sprint-wise & Type-wise defect summary with trend analysis
Total Defects |  |  |  |  | Closed |  | Open
12 |  |  |  |  | 11 |  | 1
Defects by Sprint | [5 empty] | Defects by Type
Sprint | Total | Logical | UI | Standards | Others | Type | Count | %
Sprint 1 | 3 | 2 | 0 | 1 | 0 | Logical | 6 | 50%
Sprint 2 | 4 | 2 | 1 | 0 | 1 | User Interface | 4 | 33%
Sprint 3 | 3 | 1 | 1 | 0 | 1 | Standards | 1 | 8%
Sprint 4 | 3 | 1 | 2 | 0 | 0 | Others | 1 | 8%
TOTAL | 12 | 6 | 4 | 1 | 2

## Defect Types
Defect Type Reference
Type | Description
Logical | Errors in code logic, wrong algorithm, incorrect AST traversal
User Interface | Defects in Reflex frontend components, state binding, layout
Standards | PEP8, code style, naming convention violations
Maintainability | Code readability, modularity, documentation gaps
Others | Environment, API, networking, configuration issues

## Sprint Summary
Sprint-wise Defect Summary — AI Code Reviewer
Sprint | Start Date | End Date | Total Defects | Closed | Open | Notes
Sprint 1 | 2026-02-02 | 2026-02-13 | 3 | 3 | 0 | All defects resolved. AST and style detection stabilized.
Sprint 2 | 2026-02-16 | 2026-02-28 | 4 | 4 | 0 | Groq API retry and Reflex state binding issues resolved.
Sprint 3 | 2026-03-03 | 2026-03-13 | 3 | 3 | 0 | AI JSON parsing and server socket issues fixed.
Sprint 4 | 2026-03-16 | 2026-03-28 | 3 | 2 | 1 | 1 open defect (PDF print) — deferred to next release.